## Timeline
Feature ID | Feature Name | US ID | User Story Title | Priority | Target Timeline | Status | Start Date | End Date | Notes
F1 | Destination Suggestion | US 1 | Search by city/country | High | Week 1 (05/11 - 05/17) | Not Started |  | -
F1 | Destination Suggestion | US 2 | View recommended attractions list | High | Week 1 (05/11 - 05/17) | Not Started |  | -
F3 | Trip Planner | US 1 | Set trip start and end dates | High | Week 2 (05/18 - 05/24) | Not Started |  | -
F3 | Trip Planner | US 2 | set trip dates so the planner creates the correct number of days. | High | Week 2 (05/18 - 05/24) | Not Started |  | -
F3 | Trip Planner | US 3 | Add a destination to a trip | High | Week 3 (05/25 - 05/31) | Not Started |  | -
F3 | Trip Planner | US 4 | Remove a destination from the itinerary | High | Week 3 (05/25 - 05/31) | Not Started |  | -
F2 | Destination Details | US 1 | Open a destination details view | Medium | Week 4 (06/01 - 06/07) | Not Started |  | -
F2 | Destination Details | US 2 | View photos in destination details | Medium | Week 4 (06/01 - 06/07) | Not Started |  | -
F4 | User Authentication | US 1 | Sign up with email and password | Medium | Week 5 (06/08 - 06/14) | Not Started |  | -
F4 | User Authentication | US 2 | Verify email to activate account | Medium | Week 5 (06/08 - 06/14) | Not Started |  | -
F4 | User Authentication | US 3 | Log in with email and password | Medium | Week 6 (06/15 - 06/21) | Not Started |  | -
F4 | User Authentication | US 4 | Log out | Medium | Week 6 (06/15 - 06/21) | Not Started |  | -
F3 | Trip Planner | US 5 | Require login to save trips and destinations | Medium | Week 7 (06/22 - 06/28) | Not Started |  | - | Phụ thuộc vào Feature 4
F3 | Trip Planner | US 6 | Load my saved trips and destinations when I return | Medium | Week 7 (06/22 - 06/28) | Not Started |  | - | Phụ thuộc vào Feature 4
F2 | Destination Details | US 3 | View opening hours when available | Low | Week 8 (06/29 - 07/03) | Not Started |  | - | Tuần cuối / Buffer / Demo

## template_trainee
Trainee
Current Progress | 0%
Feature ID | US ID | User Story Title | Priority | Target Deadline | Trainee Status | Actual Start | Actual End | Assessment | Mentor Feedback / Code Review Notes
F1 | US 1 | Search by city/country | High | Week 1 (05/11 - 05/17) | Not Started |  |  | To Be Evaluated
F1 | US 2 | View recommended attractions list | High | Week 1 (05/11 - 05/17) | Not Started |  |  | To Be Evaluated
F3 | US 1 | Create a trip | High | Week 2 (05/18 - 05/24) | Not Started |  |  | To Be Evaluated
F3 | US 2 | Set trip start and end dates | High | Week 2 (05/18 - 05/24) | Not Started |  |  | To Be Evaluated
F3 | US 3 | Add a destination to a trip | High | Week 3 (05/25 - 05/31) | Not Started |  |  | To Be Evaluated
F3 | US 4 | Remove a destination from the itinerary | High | Week 3 (05/25 - 05/31) | Not Started |  |  | To Be Evaluated
F2 | US 1 | Open a destination details view | Medium | Week 4 (06/01 - 06/07) | Not Started |  |  | To Be Evaluated
F2 | US 2 | View photos in destination details | Medium | Week 4 (06/01 - 06/07) | Not Started |  |  | To Be Evaluated
F4 | US 1 | Sign up with email and password | Medium | Week 5 (06/08 - 06/14) | Not Started |  |  | To Be Evaluated
F4 | US 2 | Verify email to activate account | Medium | Week 5 (06/08 - 06/14) | Not Started |  |  | To Be Evaluated
F4 | US 3 | Log in with email and password | Medium | Week 6 (06/15 - 06/21) | Not Started |  |  | To Be Evaluated
F4 | US 4 | Log out | Medium | Week 6 (06/15 - 06/21) | Not Started |  |  | To Be Evaluated
F3 | US 5 | Require login to save trips and destinations | Medium | Week 7 (06/22 - 06/28) | Not Started |  |  | To Be Evaluated
F3 | US 6 | Load my saved trips and destinations when I return | Medium | Week 7 (06/22 - 06/28) | Not Started |  |  | To Be Evaluated
F2 | US 3 | View opening hours when available | Low | Week 8 (06/29 - 07/03) | Not Started |  |  | To Be Evaluated